## Sheet1
Part 5 - Precedence Diagram Method (PDM)
Activity | Duration (days) | Predecessor | ES | EF | LS | LF
A1.1 | 8 | — | 0 | 8 | 0 | 8
A2.1 | 7 | A1.1 | 8 | 15 | 8 | 15
A2.2 | 4 | A2.1 | 15 | 19 | 15 | 19
A3.1 | 3 | A2.2 | 19 | 22 | 19 | 22
A3.2 | 3 | A3.1 | 22 | 25 | 22 | 25
A4.1 | 6 | A3.2 | 25 | 31 | 25 | 31
A5.1 | 2 | A4.1 | 31 | 33 | 31 | 33
A6.1 | 33 | A5.1 | 33 | 66 | 33 | 66
A7.1 | 4 | A6.1 | 66 | 70 | 66 | 70
A8.1 | 2 | A7.1 | 70 | 72 | 70 | 72
Step 2: Forward Pass
ES of first activity = 0
EF = ES + Duration
ES of next activity = EF of predecessor
Total project duration = 72 days
Step 3: Backward Pass
LF of last activity (A8.1) = 72
LS = LF − Duration
LF of predecessor = LS of successor
Since all activities are sequential:
ES = LS and EF = LF for all activities
Slack = 0 for all activities
Step 4: Identify the Critical Path (PDM)
## Critical Path (PDM)
- Activities with zero slack:
A1.1, A2.1, A2.2, A3.1, A3.2, A4.1, A5.1, A6.1, A7.1, A8.1
- Confirmed Critical Path:
A1.1 → A2.1 → A2.2 → A3.1 → A3.2 → A4.1 → A5.1 → A6.1 → A7.1 → A8.1
Part 6 – Schedule Crashing Analysis
Step 1: Identify Crashable Critical Activities
From the PDM, the critical path is:
A1.1 → A2.1 → A2.2 → A3.1 → A3.2 → A4.1 → A5.1 → A6.1 → A7.1 → A8.1
The highest risk activities that can be crashed are:
1. A6.1 – Develop dashboard (longest duration = 33 days)
2. A4.1 – Train model (moderate duration = 6 days)
Activity | Original Duration | Crashed Duration | Impact / Extra Resources
A6.1 – Develop dashboard | 33 | 28 | Additional developers / parallel tasks
A4.1 – Train model | 6 | 4 | Extra GPU / parallel training
Step 2: Recalculate Schedule
Forward Pass with Crashed Durations
Activity | Duration (days) | ES | EF
A1.1 | 8 | 0 | 8
A2.1 | 7 | 8 | 15
A2.2 | 4 | 15 | 19
A3.1 | 3 | 19 | 22
A3.2 | 3 | 22 | 25
A4.1 | 4 | 25 | 29
A5.1 | 2 | 29 | 31
A6.1 | 28 | 31 | 59
A7.1 | 4 | 59 | 63
A8.1 | 2 | 63 | 65
New Project Duration
Original: 72 days
After crashing: 65 days
Reduction: 7 days
Step 3: Critical Path After Crashing
Crashed activities are still on the critical path
Critical path remains unchanged:
A1.1 → A2.1 → A2.2 → A3.1 → A3.2 → A4.1 → A5.1 → A6.1 → A7.1 → A8.1
Step 4: Was Crashing Effective?
## Crashing Results
- New project duration: 65 days
- New critical path:
A1.1 → A2.1 → A2.2 → A3.1 → A3.2 → A4.1 → A5.1 → A6.1 → A7.1 → A8.1
- Was crashing effective?
Yes, because the overall project duration was reduced by 7 days. Crashing focused on the longest and most critical activities, effectively shortening the schedule without changing the critical path.